## PM Dataset
Labour monitoring and tracking during construction phase, identifying live impact on final budget and project end date
[6 empty] | Input | [7 empty] | Outputs
[6 empty] | Forecast |  |  |  |  | Actual |  |  | Deviation |  | Final Values
Phase | Task | Payment Schedule (% cumulative) | Materials (kg) | Type of Labour | Labour Rate (€/h) | Duration (no. of days) | Start Constraint | Labor Required (ppl) | Risk for Delay (holidays/weather) | End Date | Duration (no. of days) | Start Date | Actual labor (ppl) | Cost Deviation | Time Deviation | Actual Project End Date | Live Remaining Cost (£) | Overall Project End Budget (£)
Structural | Site setup | 4.5 | 420 |  | 24 | 4 | 0 | 5 | Low | 2026-06-28 | 6 | 2026-06-24 | 5 | 900 | 2 | 2026-06-30 | 982300 | 1000000
Structural | Excavation | 9.8 | 1850 |  | 28 | 9 | 4 | 7 | Medium | 2026-06-30 | 7 | 2026-06-30 | 10 | 1200 | -2 | 2026-07-07 | 964800 | 1000000
Structural | Foundations (concrete pour) | 18.6 | 14250 |  | 34 | 11 | 13 | 11 | High | 2026-07-03 | 13 | 2026-07-07 | 10 | 3600 | 2 | 2026-07-20 | 932100 | 1000000
Structural | Ground slab | 26.9 | 9650 |  | 33 | 7 | 24 | 9 | Medium | 2026-07-05 | 15 | 2026-07-20 | 5 | 4400 | 8 | 2026-08-04 | 901500 | 1000000
Structural | Structural frame (columns/slabs) | 45.7 | 28700 |  | 39 | 23 | 31 | 14 | High | 2026-07-12 | 25 | 2026-08-04 | 12 | 9300 | 2 | 2026-08-29 | 845300 | 1000000
Finishes | External walls | 58.2 | 11300 |  | 31 | 14 | 54 | 9 | Medium | 2026-07-16 | 15 | 2026-08-29 | 9 | 5800 | 1 | 2026-09-13 | 801200 | 1000000
Finishes | Roofing | 64.4 | 4700 |  | 33 | 6 | 68 | 5 | Low | 2026-07-17 | 6 | 2026-09-13 | 5 | 2500 | 0 | 2026-09-19 | 776900 | 1000000
Finishes | Windows installation | 70.3 | 2100 |  | 29 | 5 | 74 | 4 | Medium | 2026-07-18 | 4 | 2026-09-19 | 4 | 2100 | -1 | 2026-09-23 | 752600 | 1000000
Finishes | Internal plastering | 78.6 | 3850 |  | 27 | 9 | 79 | 7 | Low | 2026-07-20 | 11 | 2026-09-23 | 6 | 4300 | 2 | 2026-10-04 | 721400 | 1000000
Finishes | Floor finishes | 85.1 | 2950 |  | 26 | 7 | 88 | 5 | Low | 2026-07-22 | 9 | 2026-10-04 | 4 | 2900 | 2 | 2026-10-13 | 695200 | 1000000
Fittings | Electrical installation | 90.2 | 1400 |  | 36 | 10 | 95 | 6 | Medium | 2026-07-24 | 9 | 2026-10-13 | 6 | 3400 | -1 | 2026-10-22 | 662700 | 1000000
Fittings | Plumbing installation | 94.1 | 1650 |  | 35 | 9 | 105 | 6 | Medium | 2026-07-26 | 11 | 2026-10-22 | 5 | 4300 | 2 | 2026-11-02 | 638900 | 1000000
Fittings | HVAC installation | 97.3 | 2400 |  | 41 | 11 | 114 | 7 | High | 2026-07-29 | 15 | 2026-11-02 | 5 | 3400 | 4 | 2026-11-17 | 612500 | 1000000
Fittings | Kitchen & bathroom fittings | 99.1 | 1850 |  | 30 | 9 | 125 | 5 | Low | 2026-07-31 | 14 | 2026-11-17 | 5 | 2600 | 5 | 2026-12-01 | 590200 | 1000000
Handover | Final inspections | 99.6 | 320 |  | 28 | 4 | 134 | 3 | Low | 2026-08-01 | 7 | 2026-12-01 | 3 | 1400 | 3 | 2026-12-08 | 575600 | 1000000
Handover | Snagging & corrections | 100 | 180 |  | 27 | 5 | 138 | 4 | Medium | 2026-08-03 | 12 | 2026-12-08 | 4 | 2600 | 7 | 2026-12-20 | 12000 | 1000000
Handover | Client handover | 100 | 60 |  | 25 | 2 | 143 | 2 | Low | 2026-08-04 | 5 | 2026-12-20 | 2 | 1200 | 3 | 2026-12-25 | 0 | 1000000
Formulas:
Final Values = [End Date]+[Time Deviation]
Final Values = [Final Values, row above]+[Actual]
Start Date = [Start Date, row above]+[Actual, row above]